## #1 EV Project Fee Breakdown
Proposal for the MATS Michigan Infrastructure Office Technical Assistance Program
Fee Proposal, Work Breakdown Structure and Project Timeline
Project 1: Develop a federal discretionary grant application to fund the planning and implementation of a network of (approximately 6-12) charging stations located within the Midland Area Transportation Study Metropolitan Planning Area.
Work Breakdown Structure and Project Timeline | Project Manager | Strategy Consultant 5 | Strategy Consultant 3 | Strategy Consultant 1 | Federal Policy and Compliance Senior Advisor | Federal Policy and Compliance Technical Specialist 3 | Admin Staff | Project Controls Specialist 2 | Management Consultant 4 | Management Consultant 1 | Subject Matter Expert | Trainer 2 | Total Hours | Total Cost | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6 |  |  |  | Month 7 |  |  |  | Month 8 |  |  |  | Month 9 |  |  |  | Month 10
Task 1: Establish Project Team and Duties | [12 empty] | 58 | 8805 | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK
1. Coordinate with MATS Project Manager and MIO to finalize Scope of Work | 0 | [11 empty] | 0 | 0
2. Work with MATS Project Manager to identify full list of stakeholders and potential partners | 4 | [7 empty] | 4 |  |  |  | 8 | 1260
3. Engage key stakeholders to build relationships and leverage resources | 2 | [7 empty] | 8 |  |  |  | 10 | 1500
4. Project kick-off meeting (in-person) | 2 | [7 empty] | 2 |  |  |  | 4 | 630
5. Define roles and responsibilities of project participants | 2 | [11 empty] | 2 | 340
6. Develop project timeline with deliverables and deadlines. | 4 | [5 empty] | 4 | [5 empty] | 8 | 980
7. Ongoing weekly meetings (virtual) | 13 | [7 empty] | 13 |  |  |  | 26 | 4095
Task 2: Grant Identification / Project Management | [12 empty] | 176 | 25950
1. Review technical documents (incl. preliminary engineering guidance, traffic studies, environmental studies, cost estimates) | 2 |  | 8 | 16 |  | 8 |  |  | 16 |  |  |  | 50 | 6740
2. Review applicable MDOT, FHWA and AASHTO guidelines, policies and standards. |  |  | 2 | 8 |  |  |  |  | 8 |  |  |  | 18 | 2330
3. Review community documents (local and regional plans, equity reports, community development objectives) | 2 |  |  |  |  | 8 |  |  | 16 |  |  |  | 26 | 3820
4. Engage stakeholders to build support (local, regional, MDOT, MIO, community) |  |  | 4 |  |  | 8 |  |  | 16 |  |  |  | 28 | 4060
5. Identify which community program focus-areas the project will address and make grant application recommendations | 2 | 2 | 4 |  |  | 2 |  |  | 4 |  | 2 |  | 16 | 2710
6. Identify other potential sources of grant funding. |  |  |  |  | 4 | 4 |  |  | 16 |  |  |  | 24 | 3860
7. Select one or more federal infrastructure grant opportunities | 2 | 2 | 2 |  |  | 2 |  |  | 2 |  |  |  | 10 | 1650
8. Obtain MATS and MIO approval on grant application selection | 2 | 2 | [10 empty] | 4 | 780
0
Task 3: Grant Writing / Administration | [12 empty] | 275 | 36270
1. Select qualified staff to complete grant application process | 0 | [11 empty] | 0 | 0
2. Review grant application guidelines with staff to develop and oversee an application strategy to ensure timely submittal | 2 | [6 empty] | 2 | 2 |  |  |  | 6 | 870
3. Engage all stakeholders involved in the process. | 2 |  | 8 |  |  | 8 |  |  | 8 |  |  |  | 26 | 3820
4. Develop and distribute grant-writing schedule. | 4 | [11 empty] | 4 | 680
5. Develop grant narrative and supporting documents outlined in NOFO | 4 |  |  |  |  | 8 |  | 40 |  |  |  |  | 52 | 6640
6. Request and secure letters of support from partner agencies and elected officials. | 4 |  |  |  |  | 4 |  |  | 4 |  |  |  | 12 | 1840
7. Compile construction cost estimate and other project costs outlined in NOFO | 2 |  | 2 | 4 |  | 2 |  | 8 |  |  |  |  | 18 | 2320
8. Compile benefits (market and non-market) previously identified and develop data strategy |  |  | 4 |  |  | 4 |  |  | 4 |  |  |  | 12 | 1740
8. Locate, identify, research and collect publicly available data |  |  | 4 | 16 | [8 empty] | 20 | 2340
9. Engage stakeholders for private data sources |  |  | 8 | [9 empty] | 8 | 1160
10. Analyze data and present findings to MATS | 1 |  | 4 | 24 | [8 empty] | 29 | 3390
11. Engage stakeholders for review and feedback | 2 |  | 2 | [9 empty] | 4 | 630
12. Incorporate findings into grant project narrative | [5 empty] | 2 |  | 8 |  |  |  |  | 10 | 1250
13. Incorporate findings into additional project narrative | [5 empty] | 2 |  | 8 |  |  |  |  | 10 | 1250
14. Prepare budget report and budget justifications outlined in NOFO |  |  | 2 |  |  |  |  | 4 |  |  |  |  | 6 | 770
15. Compile documentation and full application | [7 empty] | 4 |  |  |  |  | 4 | 480
16. Perform internal NOFO compliance audit |  |  |  |  | 4 |  |  | 2 |  |  |  |  | 6 | 1200
17. Submit draft grant application proposal to MATS and key stakeholders for review | 2 | [7 empty] | 2 |  |  |  | 4 | 630
18. Incorporate comments and edits. | [5 empty] | 2 |  | 4 |  |  |  |  | 6 | 770
19. Perform final internal quality review | [5 empty] | 2 |  | 2 |  |  |  |  | 4 | 530
20. Work with MATS staff to submit final grant application | 2 |  |  |  |  | 4 | [6 empty] | 6 | 920
21. Track application status in Grants.gov and prepare RFI responses | [5 empty] | 4 |  | 8 |  |  |  |  | 12 | 1540
22. Develop training materials and provide logistical support to the local agency upon grant award | [5 empty] | 4 | 8 |  |  |  |  | 4 | 16 | 1500
Assumptions:
1. Fee proposal assumes that preliminary engineering designs and cost estimates are available for review. Engineering cost estimates are not included in this scope and fee.
2. Fee proposal assumes the availability of traffic studies, traffic data, regional traffic models, environmental impact studies, equity reports and any other reports required to assess community program focus-areas and assess grant application feasibility.
3. The gathering of additional data (not available from public or private data source) via traffic studies or other methods are not included in this scope.
4. This scope and fee assumes flexibility between tasks and people. GGA intends to execute with the key personnel identified, however, other roles may not be filled by the named individual based upon the workload at the time of project execution.
5. All meetings, except for the project kick-off meeting, will be virtual. Travel expenses for all other meetings are not included in this fee.

## #2 Bridge Project Fee Breakdown
Proposal for the MATS Michigan Infrastructure Office Technical Assistance Program
Fee Proposal, Work Breakdown Structure and Project Timeline
Project 2: Develop a federal discretionary grant application to fund the work for the Saginaw Road Bridge over the Tittabawassee River, located in Sanford, Michigan, Str. No. FHWA 7022.
Work Breakdown Structure and Project Timeline | Project Manager | Strategy Consultant 5 | Strategy Consultant 3 | Strategy Consultant 1 | Federal Policy and Compliance Senior Advisor | Federal Policy and Compliance Technical Specialist 3 | Admin Staff | Project Controls Specialist 2 | Management Consultant 4 | Management Consultant 1 | Subject Matter Expert | Trainer 2 | Total Hours | Total Cost | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6 |  |  |  | Month 7 |  |  |  | Month 8 |  |  |  | Month 9 |  |  |  | Month 10
Task 1: Establish Project Team and Duties | [12 empty] | 60 | 9095 | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK | WK
1. Coordinate with MATS Project Manager and MIO to finalize Scope of Work | 0 | [11 empty] | 0 | 0
2. Work with MATS Project Manager to identify full list of stakeholders and potential partners | 4 | [7 empty] | 4 |  |  |  | 8 | 1260
3. Engage key stakeholders to build relationships and leverage resources | 2 | [7 empty] | 8 |  |  |  | 10 | 1500
4. Project kick-off meeting (in-person) | 2 |  |  |  |  | 2 |  |  | 2 |  |  |  | 6 | 920
5. Define roles and responsibilities of project participants | 2 | [11 empty] | 2 | 340
6. Develop project timeline with deliverables and deadlines. | 4 | [5 empty] | 4 | [5 empty] | 8 | 980
7. Ongoing weekly meetings (virtual) | 13 | [7 empty] | 13 |  |  |  | 26 | 4095
Task 2: Grant Identification / Project Management | [12 empty] | 174 | 25430
1. Review design documents (incl. preliminary engineering designs and guidance, traffic studies, environmental studies, cost estimates) | 2 |  | 12 | 24 |  | 4 |  |  | 4 |  |  |  | 46 | 5880
2. Review applicable MDOT, FHWA and AASHTO guidelines, policies and standards. |  |  | 2 | 12 |  | 2 |  |  | 4 |  |  |  | 20 | 2480
3. Review community documents (local and regional plans, equity reports, community development objectives) | 2 |  |  |  |  | 8 |  |  | 16 |  |  |  | 26 | 3820
4. Engage stakeholders to build support (local, regional, MDOT, MIO, TAMC, community) |  |  | 4 |  |  | 8 |  |  | 16 |  |  |  | 28 | 4060
5. Identify other potential sources of grant funding. |  |  |  |  | 4 | 4 |  |  | 16 |  | 2 |  | 26 | 4340
6. Determine project approach (reconstruction vs. replacement) | 2 | 2 | 4 |  |  | 2 |  |  | 2 |  | 2 |  | 14 | 2420
7. Select one or more federal infrastructure grant opportunities | 2 | 2 | 2 |  |  | 2 |  |  | 2 |  |  |  | 10 | 1650
8. Obtain MATS and MIO approval on grant application selection | 2 | 2 | [10 empty] | 4 | 780
Task 3: Grant Writing / Administration | [12 empty] | 261 | 38810
1. Select qualified staff to complete grant application process | 0 | [11 empty] | 0 | 0
2. Review grant application guidelines with staff to develop and oversee an application strategy to ensure timely submittal | 2 | [6 empty] | 2 | 2 |  |  |  | 6 | 870
3. Engage all stakeholders involved in the process. | 2 |  | 8 |  |  | 8 |  |  | 8 |  |  |  | 26 | 3820
4. Develop and distribute grant-writing schedule | 4 | [11 empty] | 4 | 680
5. Develop grant narrative and supporting documents outlined in NOFO | 4 |  |  |  |  | 8 |  | 40 |  |  |  |  | 52 | 6640
6. Request and secure letters of support from partner agencies and elected officials. | 4 |  |  |  |  | 4 |  |  | 4 |  |  |  | 12 | 1840
7. Compile construction cost estimate and other project costs outlined in NOFO | 2 |  | 8 | 16 | [8 empty] | 26 | 3260
8. Compile benefits (market and non-market) previously identified and develop data strategy |  |  | 4 |  |  | 4 |  |  | 4 |  |  |  | 12 | 1740
9. Locate, identify, research and collect publicly available data |  |  | 4 | 16 | [8 empty] | 20 | 2340
10. Engage stakeholders to obtain private data sources |  |  | 8 | [9 empty] | 8 | 1160
11. Analyze data and present findings to MATS | 1 |  | 4 | 24 | [8 empty] | 29 | 3390
12. Engage stakeholders for review and feedback | 2 |  | 2 | [9 empty] | 4 | 630
13. Incorporate comments and finalize BCA |  |  | 2 | 4 | [9 empty] | 730
14. Generate BCA Report |  |  | 2 | 8 | [9 empty] | 1170
15. Incorporate data into grant narrative, including visualizations |  |  | 2 | 8 | [9 empty] | 1170
16. Prepare budget report and budget justifications outlined in NOFO |  |  |  | 4 |  |  |  | 4 | [5 empty] | 920
17. Compile documentation and full application | [7 empty] | 4 |  |  |  |  | 4 | 480
18. Perform internal NOFO compliance audit |  |  |  |  | 4 |  |  | 2 |  |  |  |  | 6 | 1200
19. Submit draft grant application proposal to MATS and key stakeholders for review | 2 | [7 empty] | 2 |  |  |  | 4 | 630
20. Incorporate comments and edits | [5 empty] | 2 |  | 4 |  |  |  |  | 6 | 770
21. Perform final internal quality review |  | 4 |  |  |  | 2 |  | 2 |  |  |  |  | 8 | 1410
22. Work with MATS staff to submit final grant application | 2 |  |  |  |  | 4 | [6 empty] | 6 | 920
22. Track application status in Grants.gov and prepare RFI responses | [5 empty] | 4 |  | 8 |  |  |  |  | 12 | 1540
23. Develop training materials and provide logistical support to the local agency upon grant award | [5 empty] | 4 | 8 |  |  |  |  | 4 | 16 | 1500
Assumptions:
1. Fee proposal assumes that preliminary engineering designs and cost estimates are available for the two proposed bridge alternatives. Engineering cost estimates are not included in this scope and fee.
2. Fee proposal assumes the availability of traffic studies, traffic data, regional traffic models, environmental impact studies, equity reports and any other reports required to analyze grant application feasibility.
3. Assumes that a static BCA sensitivity analysis will be performed. A dynamic BCA sensitivity analysis is not included.
4. The gathering of additional data (not available from public or private data source) via traffic studies or other methods are not included in this scope.
5. This scope and fee assumes flexibility between tasks and people. GGA intends to execute with the key personnel identified, however, other roles may not be filled by the named individual based upon the workload at the time of project execution.
6. All meetings, except for the project kick-off meeting, will be virtual. Travel expenses for all other meetings are not included in this fee.

## Rates
Proposal for the MATS Michigan Infrastructure Office Technical Assistance Program
Project Rates
Firm | Name | Position | Project Rate | Hourly Rate (Not to Exceed) in Pre-Qualification
GGA | Constantine Deir, PE | Project Manager | 170 | 275
AECOM | Lincoln James | Strategy Consultant 5 | 220 | 240
AECOM | Carey Barr, PE | Strategy Consultant 3 | 145 | 155
AECOM | TBD (Subcontract) | Strategy Consultant 1 | 110 | 115
AECOM | Nicole Boothman-Shepard | Federal Policy and Compliance Senior Advisor | 240 | 269
Franklin Associates | Brandy Bones | Federal Policy and Compliance Technical Specialist 3 | 145 | 170
GGA | TBD | Admin Staff | 75 | 92
GGA | Constantine Deir, PE | Project Controls Specialist 2 | 120 | 165
GGA | Josh Schneider | Management Consultant 4 | 145 | 175
GGA | Leah Shaffer | Management Consultant 1 | 80 | 100
AECOM | Toni A. Horst, PhD | Subject Matter Expert | 240 | 265
GGA | TBD | Trainer 2 | 80 | 140